## Sheet 1
Table 1
|  | Mendocino Community Center Fence Replacement |  | Schedule as of 10/24/25
|  | Tasks | Dimensions | Time | Team | Comment
Date | Task
Ongoing offsite |  | Prime and paint posts, stringers and pickets for first 45’ of School St fence | 45’ of fence: 7 posts, 12 stringers, 120 pickets | NA | Matt
Underway | 1 | Purchase about 1/2 of materials |  | NA | On order
Ongoing offsite | 2 | Cut, lightly sand, prime and paint lumber for second 75’ of School St fence | 75’ of fence: 11 posts, 20 stringers, 202 pickets | NA | Jeff and John (cut and sand) Matt (prime and paint)
Wednesday November 5 | 3 | Place 120’ of protective fence, demolish and remove existing fence along School St. |  | 1:30-4:30 | Jeff and ??? Matt and crew
Thursday November 6 | 4 | Place alignment and elevation lines, mark location of new post holes |  | 8:30-10:30 | Jeff and Matt
Friday November 7 | 5 | Dig 7 post holes for first 45’ of fence |  | 8:00-11:00 | Matt and Crew
Saturday November 8 | 6 | Place posts and stringers, gravel and concrete |  |  | Jeff and ??? | Need 3 or 4 persons
Saturday November 15 | 7 | Place pickets and screw to stringers |  |  | Jeff and ??? | Need 3 or 4 persons
Thursday November 20 | 8 | Place alignment and elevation lines, mark location of new post holes |  | 8:00-9:00 | Jeff and Matt
Friday November 21 | 9 | Dig 11 post holes for second 75’ of fence |  | 8:00-11:00 | Matt and crew
Saturday November 22 | 10 | Place posts and stringers, gravel and concrete |  | 8:00-11:00 | Jeff and ??? | Need 3 or 4 persons
Saturday November 29 | 11 | Place pickets and screw to stringers |  | 11:00-12:00 | All hands | Need 3 or 4 persons
First week of December | 12 | Remove protective fence |  | Varies | Jeff and ???